## Slide 1
ALI BAYOUMI
INDEPENDENT PORTFOLIO CASE STUDY
Planning &
Project Controls
G+9 office building + roof
Primavera P6 / Baseline, update and management reporting
SIMULATED PROJECT · REPORTING DATA DATE 01 APR 2027
Notes: This independent case study demonstrates how I built and interpreted a complete planning and project-controls model. Quantities, rates and progress are simulated. The portfolio presents the audited original snapshot, not a newly recalculated cleanup candidate.
[Sources]
Ali_Bayoumi_Planning_Project_Controls_Portfolio.pptx (corrected version 2, 07 September 2026)
Ali_Bayoumi_Portfolio_Audit.pdf (07 September 2026) — pp. 1, 3–4
All project values are from the preserved simulated P6 snapshot with data date 01-Apr-2027. No fresh P6 schedule or leveling run is claimed.
[/Sources]

## Slide 2
PROGRAMME SCALE
A complete building programme
ALI BAYOUMI / PRIMAVERA P6 CASE STUDY
SIMULATED PROJECT
02
1,206
scheduled activities
G+9 + roof
Engineering through handover
1,876
logic relationships
195
WBS nodes, including project root
33
resources
Engineering · Procurement · Construction · MEP · Finishes · External works · Handover
Notes: The scale is 1,206 activities, 1,876 original relationships, 195 WBS nodes including the project root and 33 resources. Activity mix is 1,073 tasks, 130 milestones and three LOE activities. The separate cleanup candidate has 1,875 links; it is not the snapshot being presented.
[Sources]
Ali_Bayoumi_Planning_Project_Controls_Portfolio.pptx (corrected version 2, 07 September 2026)
Ali_Bayoumi_Portfolio_Audit.pdf (07 September 2026) — pp. 3, 6
All project values are from the preserved simulated P6 snapshot with data date 01-Apr-2027. No fresh P6 schedule or leveling run is claimed.
[/Sources]

## Slide 3
CONTROL METHOD
One reporting cut connects the model
ALI BAYOUMI / PRIMAVERA P6 CASE STUDY
SIMULATED PROJECT
03
Data date: 01 Apr 2027. Dates, cost and resources are reconciled before reporting.
01 / Establish
Baseline & status
Preserve the original baseline.
Update actuals and remaining work to the data date.
02 / Calculate
CPM & resources
Reschedule the logic.
Review resource leveling and preserved early / late dates.
03 / Interpret
Value & priorities
Reconcile earned value.
Issue the critical-path, cost, resource and lookahead reports.
Notes: The case study update cycle has six actions: preserve the baseline, status to the data date, reschedule CPM, level resources, measure EV and issue reports. The display groups them into three stages without changing that method. This presentation uses the saved outputs; no new native run took place during the redesign.
[Sources]
Ali_Bayoumi_Planning_Project_Controls_Portfolio.pptx (corrected version 2, 07 September 2026)
Ali_Bayoumi_Portfolio_Audit.pdf (07 September 2026) — pp. 1, 4, 6
All project values are from the preserved simulated P6 snapshot with data date 01-Apr-2027. No fresh P6 schedule or leveling run is claimed.
[/Sources]

## Slide 4
STATUS AT DATA DATE
276 activities complete; 930 remain open
ALI BAYOUMI / PRIMAVERA P6 CASE STUDY
SIMULATED PROJECT
04
Chart: 
| Complete | In progress | Not started
Activities | 276 | 9 | 921
01 APR 2027
A single status snapshot
across the integrated programme.
9
activities in progress
Counts describe activity status. They are not a weighted physical-progress percentage.
Notes: 276 + 9 + 921 = 1,206. The 930 incomplete activities are the denominator used in the float screens. An activity-count completion percentage would not establish physical progress and is intentionally not presented.
[Sources]
Ali_Bayoumi_Planning_Project_Controls_Portfolio.pptx (corrected version 2, 07 September 2026)
Ali_Bayoumi_Portfolio_Audit.pdf (07 September 2026) — p. 3
All project values are from the preserved simulated P6 snapshot with data date 01-Apr-2027. No fresh P6 schedule or leveling run is claimed.
[/Sources]

## Slide 5
FINISH FORECAST
Keep the three finish dates distinct
ALI BAYOUMI / PRIMAVERA P6 CASE STUDY
SIMULATED PROJECT
05
Final project handover: saved early dates and leveled dates answer different questions.
15 AUG 2028
CPM early finish
Preserved scheduled early date in the source snapshot.
16 AUG 2028
Leveled handover
Current HO-023 remaining / leveled finish.
22 AUG 2028
Baseline handover
Original baseline HO-023 finish. Use the same milestone scope.
Saved comparison: leveled handover is 6 calendar days before baseline. This is not a tested recovery claim.
Notes: All three finishes are at 18:00. Baseline HO-023 handover is 22-Aug-2028; a different stored project ScheduledFinishDate is 02-Aug-2028 and must not be substituted. Preserve Scheduled Early and Late Dates is enabled. Timeline columns show the field sequence, not time-proportional spacing.
[Sources]
Ali_Bayoumi_Planning_Project_Controls_Portfolio.pptx (corrected version 2, 07 September 2026)
Ali_Bayoumi_Portfolio_Audit.pdf (07 September 2026) — p. 4
All project values are from the preserved simulated P6 snapshot with data date 01-Apr-2027. No fresh P6 schedule or leveling run is claimed.
[/Sources]

## Slide 6
EARNED VALUE
The EVM totals reconcile to the source
ALI BAYOUMI / PRIMAVERA P6 CASE STUDY
SIMULATED PROJECT
06
Cumulative value at 01 Apr 2027 · USD thousands
Chart: 
| PV | EV | AC
USD thousands | 923.0423 | 927.4769 | 940.0423
1.0048
SPI = EV / PV
0.9866
CPI = EV / AC
PV $923,042.33 · EV $927,476.92 · AC $940,042.33
Notes: The exact values reconcile to OFF-04 to the cent. SV is EV minus PV = +4,434.59; CV is EV minus AC = -12,565.41. EV is duration-based and actuals are simulated / auto-computed; reconciliation does not independently validate production or invoices. The native chart stores the exact values in thousands; labels round to one decimal.
[Sources]
Ali_Bayoumi_Planning_Project_Controls_Portfolio.pptx (corrected version 2, 07 September 2026)
Ali_Bayoumi_Portfolio_Audit.pdf (07 September 2026) — p. 2
All project values are from the preserved simulated P6 snapshot with data date 01-Apr-2027. No fresh P6 schedule or leveling run is claimed.
[/Sources]

## Slide 7
PERFORMANCE INTERPRETATION
The SPI gain is entirely reporting LOE
ALI BAYOUMI / PRIMAVERA P6 CASE STUDY
SIMULATED PROJECT
07
+$4,434.59
Schedule variance
Produced by PM-038
Monthly Progress Reporting
Value in PM-038 | USD
Planned value | 96,452.33
Earned value | 100,886.92
Outside this LOE
PV = EV = $826,590.00
Positive SPI alone does not establish construction progress ahead of plan.
Notes: PM-038 budget is $500,000. Its baseline elapsed work is 696 of 3,608 hours (19.2905%); current duration percent is 20.1774%. This produces the entire positive SV. Outside PM-038, planned and earned values are identical. That is the reason to resist a superficial construction-ahead statement.
[Sources]
Ali_Bayoumi_Planning_Project_Controls_Portfolio.pptx (corrected version 2, 07 September 2026)
Ali_Bayoumi_Portfolio_Audit.pdf (07 September 2026) — p. 2
All project values are from the preserved simulated P6 snapshot with data date 01-Apr-2027. No fresh P6 schedule or leveling run is claimed.
[/Sources]

## Slide 8
COST CONTROL
Two completed activities explain the overrun
ALI BAYOUMI / PRIMAVERA P6 CASE STUDY
SIMULATED PROJECT
08
Completed foundation work · USD
Chart: 
| CIV-013 | CIV-017
Budget | 53368 | 63022
Actual | 60868 | 72522
$17,000
overrun retained in EAC
CIV-013 +$7,500
CIV-017 +$9,500
EAC $5,268,281
BAC $5,251,281
Configured forecast: EAC = actual cost + remaining cost. Both completed activities have zero ETC.
Notes: CIV-013 has BAC 53,368 and AC 60,868; CIV-017 has BAC 63,022 and AC 72,522. Both are completed foundation reinforcement / concrete work and have zero remaining cost. EAC = 940,042.33 + 4,328,238.67 = 5,268,281; VAC = BAC - EAC = -17,000. BAC/CPI would be a separate sensitivity, not this configured forecast.
[Sources]
Ali_Bayoumi_Planning_Project_Controls_Portfolio.pptx (corrected version 2, 07 September 2026)
Ali_Bayoumi_Portfolio_Audit.pdf (07 September 2026) — p. 2
All project values are from the preserved simulated P6 snapshot with data date 01-Apr-2027. No fresh P6 schedule or leveling run is claimed.
[/Sources]

## Slide 9
STRUCTURAL SEQUENCE
Protect the pour, then the full handover
ALI BAYOUMI / PRIMAVERA P6 CASE STUDY
SIMULATED PROJECT
09
Ground-floor milestones need both the current finish and the correct baseline reference.
09 APR 2027
Column curing
GF-ST-007
192 hours remaining
Total float: 9 hours
25 APR 2027
Beam / slab pour
GF-ST-015
Baseline: 19 Apr 2027
6 calendar days later
05 MAY 2027
Structural handover
GF-ST-019
Baseline: 01 May 2027
4 calendar days later
Formwork → reinforcement → sleeves → inspection → pour. Validate curing and floor-release assumptions.
Notes: GF-ST-007 finish is 09-Apr-2027 00:00 on a 24/7 calendar. Pour and handover are at 18:00. OFF-06 is an eight-activity filtered extract ending at the pour; it is not the full ground-floor scope or proof of the entire project longest path. Seven reported BL1 dates differ from the XML baseline; the baseline comparisons shown here use baseline 4516. Review 96-hour lag purpose and next-floor start tied to the pour +8h before changing the engineering assumptions. Timeline columns group gates, not proportional durations.
[Sources]
Ali_Bayoumi_Planning_Project_Controls_Portfolio.pptx (corrected version 2, 07 September 2026)
Ali_Bayoumi_Portfolio_Audit.pdf (07 September 2026) — pp. 4–5
All project values are from the preserved simulated P6 snapshot with data date 01-Apr-2027. No fresh P6 schedule or leveling run is claimed.
[/Sources]

## Slide 10
RESOURCE CONTROL
Leveling needs more than a finish date
ALI BAYOUMI / PRIMAVERA P6 CASE STUDY
SIMULATED PROJECT
10
33 resources · 572 assignments
Chart: 
| Labor crews | Equipment | Materials
Resources | 19 | 4 | 10
31
direct resource delays in the log
222
incomplete activities with different
saved early and remaining dates
These are different measures. The log also records 469 predecessor delays and zero unable to level.
Notes: Resources are 19 labor crews, four equipment resources and ten materials. Crew units cannot be translated to headcount without resource definitions. The Office-1 log reports 31 direct delays, 469 predecessor delays and zero unlevelable activities. The offline source comparison finds 222 incomplete activities with different early / remaining dates. A single-project saved-assignment screen found no nominal labor capacity excess, but this is not a complete native leveling rerun with the external resource environment.
[Sources]
Ali_Bayoumi_Planning_Project_Controls_Portfolio.pptx (corrected version 2, 07 September 2026)
Ali_Bayoumi_Portfolio_Audit.pdf (07 September 2026) — p. 6
All project values are from the preserved simulated P6 snapshot with data date 01-Apr-2027. No fresh P6 schedule or leveling run is claimed.
[/Sources]

## Slide 11
EXECUTION LOOKAHEAD
The next 90 days define the workfronts
ALI BAYOUMI / PRIMAVERA P6 CASE STUDY
SIMULATED PROJECT
11
01 APR → 30 JUN 2027
189 rows
Procurement finish gates in the saved lookahead
Package | Manufacture | FAT | Delivery | Approval
HVAC / Electrical / Plumbing / Low current | 14 Apr | 19 Apr | 03 May | 09 May
Fire fighting | 21 Apr | 26 Apr | 10 May | 16 May
Coordinate GF structure, masonry, MEP first-fix readiness and repetitive floor production.
Notes: All table dates are finish gates in 2027 from the original OFF-07 page-one extract embedded in the corrected portfolio. Manufacturing is followed by FAT, delivery, inspection and approval; the table shows selected finish gates and does not remove inspection from the sequence. The corrected April–June analytical filter includes all June 30 starts: 189 rows rather than 186. Added activities are FL1-IP-003, GF-MEPSF-006 and GF-MEPSF-007. Source filter: Status not Completed; Start < 01-Jul-2027; Finish >= 01-Apr-2027.
[Sources]
Ali_Bayoumi_Planning_Project_Controls_Portfolio.pptx (corrected version 2, 07 September 2026)
Ali_Bayoumi_Portfolio_Audit.pdf (07 September 2026) — pp. 4, 7
All project values are from the preserved simulated P6 snapshot with data date 01-Apr-2027. No fresh P6 schedule or leveling run is claimed.
[/Sources]

## Slide 12
SCHEDULE QUALITY
The audit makes model limitations visible
ALI BAYOUMI / PRIMAVERA P6 CASE STUDY
SIMULATED PROJECT
12
Diagnostic | Source result | What it means
Network integrity | 0 cycles / broken references | A connected graph still needs sound handoffs.
Incomplete activity float | 184 zero; 496 high float | Review finish control and interfaces.
Relationship logic | 112 positive lags; 12 SS-only exits | Confirm lag purpose and finish handoffs.
GF report baseline | 7 of 8 BL1 rows differ | Use XML baseline 4516 for comparison.
Calendars / cost coverage | Open assumptions | Validate exceptions and package mapping.
High float is screened above 44 own-calendar working days. These are diagnostics, not a DCMA compliance score.
Notes: Audit findings: no cycles, broken references or exact duplicate relationship types; two intended open endpoints, NTP and final handover; no constraints, expected finishes or future actuals. Among 930 incomplete activities, 184 have zero float and 496 exceed 44 own-calendar working days. Twelve activities only have SS successors. The redundant SF link has a separate one-link cleanup candidate; it is not adopted in this presentation. No 2026–2028 holiday exceptions were found. 708 activities have neither assignment nor expense and need a package-to-cost mapping to evaluate coverage.
[Sources]
Ali_Bayoumi_Planning_Project_Controls_Portfolio.pptx (corrected version 2, 07 September 2026)
Ali_Bayoumi_Portfolio_Audit.pdf (07 September 2026) — pp. 3, 5–8
All project values are from the preserved simulated P6 snapshot with data date 01-Apr-2027. No fresh P6 schedule or leveling run is claimed.
[/Sources]

## Slide 13
MANAGEMENT RESPONSE
Three actions drive the next update
ALI BAYOUMI / PRIMAVERA P6 CASE STUDY
SIMULATED PROJECT
13
01
Protect structure
Confirm curing, stripping and next-floor release assumptions. Track the pour and full GF handover separately.
02
Release MEP gates
Track manufacture, FAT, delivery, inspection and approval. Keep June 30 starts inside the lookahead.
03
Control exceptions
Explain completed-work overruns. Reconcile leveling delays and correct the report baseline assignment.
Notes: The proposed next update should resolve assumptions, preserve the baseline and regenerate the native outputs before making new date or performance claims. Structural method / temporary works confirmation, procurement evidence and explanation of actual-cost variance are the operational priorities. Any cleanup candidate needs a separate-project import, F9 and leveling run, with logs retained. These are recommended next actions, not claims that they have already been completed.
[Sources]
Ali_Bayoumi_Planning_Project_Controls_Portfolio.pptx (corrected version 2, 07 September 2026)
Ali_Bayoumi_Portfolio_Audit.pdf (07 September 2026) — pp. 5, 7–9
All project values are from the preserved simulated P6 snapshot with data date 01-Apr-2027. No fresh P6 schedule or leveling run is claimed.
[/Sources]

## Slide 14
REPORTING EVIDENCE
The reporting pack stays linked to the model
ALI BAYOUMI / PRIMAVERA P6 CASE STUDY
SIMULATED PROJECT
14
Original P6 output
OFF-04 · Earned Value Summary · 01 Apr 2027
The source amounts underpin the editable EVM charts and the variance analysis.
Five P6 reports
Labor crew loading
Earned value summary
PV / EV / AC curve
GF structural extract
90-day lookahead
Original outputs are retained alongside the corrected analytical comparisons.
Notes: The embedded picture is an enlarged crop of the original OFF-04 report image from the corrected source PowerPoint, retained as documentary evidence. It shows the planned, earned and actual value columns. The original image bytes remain embedded and the crop is editable in PowerPoint. The main EVM charts elsewhere are native editable charts. A PV/EV/AC curve is not a commercial cash-flow forecast because payment terms, receipts and timing were not modeled. Five reports in the source pack are OFF-03 through OFF-07.
[Sources]
Embedded asset: ppt/media/image3.png from the corrected source portfolio; original OFF-04 Update 01 – Earned Value Summary.
[/Sources]
[Sources]
Ali_Bayoumi_Planning_Project_Controls_Portfolio.pptx (corrected version 2, 07 September 2026)
Ali_Bayoumi_Portfolio_Audit.pdf (07 September 2026) — pp. 2, 6, 9
All project values are from the preserved simulated P6 snapshot with data date 01-Apr-2027. No fresh P6 schedule or leveling run is claimed.
[/Sources]

## Slide 15
PORTFOLIO HANDOFF
A model that can be explained and defended
ALI BAYOUMI / PRIMAVERA P6 CASE STUDY
SIMULATED PROJECT
15
Build the logic.
Reconcile the story.
Define the next action.
SOURCE MODEL
Current-project XER
XML with the original baseline
CONTROL OUTPUTS
Five P6 reports
Corrected analytical extracts
TECHNICAL DEFENSE
Audit and reconciliation
Documented assumptions
Notes: This case study demonstrates WBS and CPM construction, baseline and update governance, resource loading and leveling interpretation, earned value and completion forecasting, structural / near-critical review and lookahead reporting. The current XER contains no embedded baseline; the supplied XML archive includes it. The work is an independent simulation, not client-approved delivery, certified actuals or a fresh P6 forecast. All source artifacts listed are in the original portfolio package, rather than embedded working P6 files inside this presentation.
[Sources]
Ali_Bayoumi_Planning_Project_Controls_Portfolio.pptx (corrected version 2, 07 September 2026)
Ali_Bayoumi_Portfolio_Audit.pdf (07 September 2026) — pp. 1, 9
All project values are from the preserved simulated P6 snapshot with data date 01-Apr-2027. No fresh P6 schedule or leveling run is claimed.
[/Sources]

## Slide 16
TRAINING 01 / PRACTICE EXERCISE
Contractor Programme Review
Independent training exercise using assumed events and data; not a live contractual claim.
ALI BAYOUMI / CONSULTANT REVIEW TRAINING
16
C-01 Calendar exceptions require confirmation
Review item | Observation and requested response
Source finding | The saved programme has no holiday exceptions for 2026–2028.
Potential effect | Work could fall on dates when crews are unavailable. The time impact is unquantified.
Review comment | Submit the agreed holiday and shutdown calendar. Explain any continuous-work calendars.
Required action | Planner: update a copy, recalculate CPM and compare the same handover milestone.
Training response due: 02 Apr 2027. Status: open pending evidence.
Notes: Source: existing portfolio slide 12 and its speaker notes, preserved simulated update dated 01 Apr 2027. The review comment and response deadline below are training additions.
Talk track: I would first confirm whether the omission is intentional. Continuous curing and site labor can legitimately use different calendars. I request approved working-time assumptions before inserting holidays. I preserve the submitted programme, update a separate copy and compare the same milestone after a native schedule run. I record the response and retain the calculation log. A missing exception is a review query, not proof of a specific completion delay. I have not rerun the full P6 model for this exercise.
Question: How many days does this finding delay handover? Answer: The saved evidence does not establish that. The approved calendar, affected activities and recalculated controlling path are needed.
Independent training exercise using assumed events and data; not a live contractual claim.

## Slide 17
TRAINING 02 / ASSUMED QUANTITIES
Progress Verification & Reporting
Independent training exercise using assumed events and data; not a live contractual claim.
ALI BAYOUMI / CONSULTANT REVIEW TRAINING
17
Slab package: 400 m³ total scope. Reporting cut: 01 Apr 2027.
Reporting basis | Quantity | Progress | Training evidence
Planned to date | 200 m³ | 50% | Assumed quantity plan
Contractor reported | 180 m³ | 45% | Assumed daily report
Verified in exercise | 160 m³ | 40% | Mock Q-001 + IR-001
−10 percentage points
Verified vs planned. Quantity shortfall: 40 m³.
Log | Finding | Action owner / response | Due
D-01 | 40 m³ below plan | Site manager: submit recovery plan | 02 Apr 2027
V-01 | 20 m³ unverified | Site engineer: reconcile records | 02 Apr 2027
Notes: All quantities, record IDs, actions and dates on this slide are assumed training data. Mock Q-001 is an assumed jointly measured quantity sheet totalling 160 m³. Mock IR-001 is an assumed inspection release covering that quantity. No real or fabricated signed records are supplied.
Calculation: planned 200/400 = 50%; reported 180/400 = 45%; verified 160/400 = 40%. Verified minus planned = -10 percentage points, or -40 m³. Reported minus verified = 20 m³. The unverified quantity is not automatically rejected work. Reconcile the measurement and acceptance cut-off before recognising it. Both log entries remain open.
Measurement rule: recognise installed and accepted concrete quantities against the same 400 m³ scope. Reconcile delivery tickets, location-tagged daily records, measurements and inspection releases. Do not mix unaccepted quantities with accepted quantities or compare different cut-offs.
Question: Does 40% describe the whole P6 project? Answer: No. It is only the assumed slab package. Whole-project progress needs documented weighting across packages and consistent measurement rules. The existing P6 EV is duration-based, so this physical percentage does not replace its earned-value calculation. A production shortfall alone does not establish a delay to handover.
Independent training exercise using assumed events and data; not a live contractual claim.

## Slide 18
TRAINING 03 / ISOLATED CPM MODEL
Delay Analysis: Illustrative TIA
Independent training exercise using assumed events and data; not a live contractual claim.
ALI BAYOUMI / CONSULTANT REVIEW TRAINING
18
Model data date: 05 Apr 2027, 08:00. Mon–Fri, 8h/day, no holidays.
Release
0d
→
Clarification
4d event
→
Install
10d
→
Test
3d
→
Handover
0d
Inserted fragnet: clarification before installation. All links FS, zero lag.
Remaining work | Before event | After event
Installation, 10 working days | 05–16 Apr 2027 | 09–22 Apr 2027
Testing, 3 working days | 19–21 Apr 2027 | 23–27 Apr 2027
Training handover, M-TR01 | 21 Apr 2027, 17:00 | 27 Apr 2027, 17:00
Impact: +4 working days / +6 calendar days
EOT review also needs the contract, event responsibility and supporting records.
FIDIC procedure learning: confirm form, edition and Particular Conditions.
Notes: This simplified prospective TIA uses an assumed current update, not the original 1,206-activity P6 programme. No change to HO-023 or the main project forecast is asserted. The output is an independently calculated CPM training model, not a native P6 scheduling run.
Assumptions: data date 05 Apr 2027 at 08:00; enabling work before this date is complete. All remaining activities are unstarted. Monday–Friday calendar, 08:00–12:00 and 13:00–17:00, no holidays. FS links with zero lag, no date constraints, no resource limits or leveling, no concurrency, mitigation or acceleration. A parallel documentation activity takes 8 working days from release, finishes 14 Apr 2027 and must also precede handover. Its float is 5 working days before the event and 9 afterwards.
Network before: release to installation (10d), testing (3d), M-TR01 handover. Parallel release to documentation (8d) to handover. Network after: insert E-01 design clarification (4 working days, 05–08 Apr) between release and installation. Documentation stays unchanged. Original remaining controlling duration max(10+3,8)=13 days. Impacted duration max(4+10+3,8)=17 days. Difference=4 working days. Handover moves from 21 Apr at 17:00 to 27 Apr at 17:00, six calendar days.
Question: Does any four-day event cause four days of completion delay? Answer: No. Here the insertion affects the controlling path with zero float. Float, parallel paths, calendar changes and mitigation can change the result.
Procedure learning scope: Introductory knowledge of FIDIC-based contract procedures. Identify the contract form, edition and Particular Conditions before checking event allocation, notices, records and assessment. No clause numbers or notice periods are assumed. The model supports EOT review but does not establish entitlement or compensation.
Method reference: Society of Construction Law, Delay and Disruption Protocol, 2nd edition (2017), Part B 4.3 and 11.6(b): https://www.scl.org.uk/sites/default/files/documents/SCL_Delay_Protocol_2nd_Edition_Final.pdf
Contract context: FIDIC Golden Principles (2019), discussion of Particular Conditions: https://fidic.org/books/fidic-golden-principles-2019
Independent training exercise using assumed events and data; not a live contractual claim.